GAME DEVELOPMENT PROPOSAL

Ultimate Sugar Rush

A cozy merge, cooking, and café-renovation game for Android

| PROJECT | Ultimate Sugar Rush |
| --- | --- |
| PLATFORM | Android |
| TECHNOLOGY | Godot 4.x + Android Studio |
| PREPARED | August 3, 2026 |

Vision  •  Vertical Slice  •  Production Roadmap  •  Release Readiness

# 1. Executive Summary

Ultimate Sugar Rush is a portrait-oriented Android game that combines the immediate satisfaction of merging items with the creativity of preparing pastries and drinks and the long-term reward of restoring a warm neighborhood bakery and café. Players merge ingredients, operate cooking stations, fulfill customer orders, discover recipes, and use their earnings to personalize and expand the café.

This proposal recommends a code-first production model built in Godot 4.x and integrated with the existing Android Studio project. Godot will own gameplay, user interface, animation, audio, and content systems. Android Studio will remain the application host and release layer, handling packaging, signing, lifecycle behavior, Play services, notifications, billing, and store distribution.

PROPOSAL OBJECTIVE Deliver a polished, scalable vertical slice first, then expand through data-driven recipes, levels, customers, and renovations without repeatedly rebuilding the core architecture.

## Project outcomes

A complete, touch-first merge and cooking loop suitable for Android phones.

A cozy café metagame that turns level rewards into visible, player-selected improvements.

A maintainable content pipeline for adding recipes, merge chains, customers, levels, and story chapters.

A production-ready Android build pipeline capable of generating signed APK and AAB artifacts.

An accessible, offline-first foundation that can later support optional platform services and ethical monetization.

## Recommended initial scope

The first development commitment should be a compact vertical slice: a 6×8 merge board, lemonade and cupcake chains, an oven and blender, three customer types, five introductory levels, one renovation choice, local saving, settings, accessibility basics, and Android APK/AAB builds. This slice tests every major architectural boundary while keeping content production controlled.

# 2. Game Description and Creative Direction

## Game concept

The player inherits or discovers a neglected neighborhood café and gradually brings it back to life. Each playable level begins with a merge board containing basic ingredients and generators. By combining matching items, the player creates higher-tier ingredients and prepared goods. Those items feed cooking stations and customer orders. Successful service earns coins, reputation, recipes, and renovation currency that transform the café between levels.

## Core player fantasy

Create delightful food, make customers happy, and build a café that feels personally yours. The experience should feel comforting and expressive rather than stressful or punitive.

## Target experience

| Dimension | Direction |
| --- | --- |
| Genre | Cozy merge puzzle, cooking, light time management, and café decoration |
| Platform | Android phones; portrait orientation; touch-first controls |
| Session length | Approximately 3–8 minutes per level, with optional longer café sessions |
| Audience | Casual and cozy-game players who enjoy food, collecting, decorating, and gentle progression |
| Tone | Warm, playful, welcoming, colorful, and optimistic |
| Business model | Premium or ethical free-to-play options; no design dependency on aggressive monetization |

## Core gameplay loop

Enter a level and review customer orders or level objectives.

Generate and merge ingredients into higher-tier items.

Use cooking stations to turn ingredients into pastries, baked goods, and drinks.

Serve customers, earn rewards, and complete the level goal.

Spend rewards on recipes, upgrades, and café renovation choices.

Return with new capabilities, customers, and story objectives.

DESIGN PRINCIPLE Progress should be visible in both systems and scenery: players unlock new ways to play while watching their café become warmer, busier, and more personal.

# 3. Feature Scope

## Core launch features

| Feature Area | Planned Capability |
| --- | --- |
| Merge board | Drag-and-drop placement, configurable grids, item generators, tiered merge chains, blocked cells, selling/removal, deadlock recovery, board saving, and satisfying feedback. |
| Cooking stations | Ovens, mixers, blenders, tea brewers, and topping counters with queues, recipes, upgrades, and clear collection states. |
| Recipes | Data-driven ingredient requirements, recipe discovery, mastery, quality bonuses, and a collectible cookbook. |
| Customers | Order generation, preferences, patience/satisfaction, tips, returning regulars, named characters, and special requests. |
| Levels | Composable goals covering recipes, orders, earnings, merge tiers, satisfaction, moves, time, and special scenarios. |
| Café progression | Renovation stages, decoration choices, station upgrades, room unlocks, reputation, and persistent visual customization. |
| Narrative | Short skippable dialogue scenes, character arcs, neighborhood stories, recipe origins, and localization-ready text. |
| Rewards and economy | Coins, renovation currency, boosters, mastery rewards, achievements, and carefully balanced sources and sinks. |
| Persistence | Versioned local saves, atomic writes, backup recovery, autosave, migration support, and offline-first play. |
| Accessibility | Reduced motion, color-independent cues, audio and haptic controls, larger text options, tutorial replay, and alternative placement input. |

## Recommended additions

A garden or windowsill where players grow lemons, berries, herbs, and tea leaves.

A café mascot with cosmetic unlocks and small nonessential bonuses.

A display case that showcases favorite or mastered pastries.

A customer memory book with portraits, preferences, and story moments.

Friendship levels for recurring customers and optional character quests.

Weekly recipe challenges and seasonal decoration themes without punishing missed participation.

Day-and-night ambience tied to story progression rather than real-world waiting.

A photo mode for sharing completed café layouts.

## Features intentionally deferred

Online accounts, social visits, competitive leaderboards, live events, advertisements, and complex premium economies should remain outside the vertical slice. They introduce operational, privacy, balance, and platform complexity before the core game has proven fun.

# 4. Technical Approach

## Architecture

The existing Android Studio project will remain the authoritative Android application. The Godot project will live in a dedicated /game directory and export a PCK content pack into the app’s assets during the Gradle build. The Android activity will host the Godot engine through the official Godot Android library.

| Layer | Responsibilities |
| --- | --- |
| Android host | Application lifecycle, manifest, permissions, safe areas, immersive mode, signing, APK/AAB packaging, and Play Store delivery. |
| Platform bridge | Haptics, notifications, review prompts, achievements, cloud saves, billing, analytics, and crash reporting through narrow interfaces. |
| Godot runtime | Scenes, gameplay state, merge rules, stations, customers, level logic, animation, audio, navigation, and in-game user interface. |
| Content layer | Items, merge chains, recipes, customers, dialogue, levels, rewards, renovations, tutorials, and localization keys. |
| Build and QA | PCK generation, asset copying, Android builds, content validation, automated tests, device tests, and release artifacts. |

## Proposed repository structure

UltimateSugarRush/
  app/                      Android host application
  game/                     Godot source project
    scenes/                 Screens, gameplay, UI, and reusable components
    scripts/                Gameplay and service logic
    data/                   Recipes, levels, customers, and balancing
    art/ and audio/         Source-ready game assets
    tests/                  Gameplay and content tests
  tools/                    Build and validation utilities
  docs/                     Design, technical, and production documentation

## Engineering principles

Data-driven content: new recipes and levels should rarely require changes to core code.

Offline-first behavior: gameplay and saves must not depend on network availability.

Platform isolation: Android services use a thin bridge with safe no-op fallbacks.

Versioned persistence: every save schema change includes an explicit migration path.

Deterministic logic: merge and level simulations support reproducible tests and balancing.

Performance by design: bounded effects, pooled objects, controlled texture memory, and no avoidable per-frame allocation.

# 5. Production Tools

The toolchain keeps game production code-first while preserving professional Android release workflows and a scalable content pipeline.

| Tool | Role | Use in This Project |
| --- | --- | --- |
| Godot 4.x | Primary game engine | 2D scenes, gameplay, touch input, UI, animation, particles, audio, resource loading, and Android-compatible runtime. |
| GDScript | Gameplay language | Fast iteration, close integration with Godot, readable systems, and simpler Android deployment than a C# dependency chain. |
| Android Studio | Android host and release IDE | Gradle configuration, manifest, platform bridge, Logcat, device debugging, signing, APK/AAB builds, and Play services. |
| Gradle / Kotlin DSL | Build automation | Pins dependencies, generates the Godot PCK, copies assets, assembles variants, runs tests, and prepares release artifacts. |
| Java | Existing Android host language | Hosts the engine and implements initial Android-facing integrations without requiring an immediate language migration. |
| JSON / Godot Resources | Content definitions | Stores merge chains, recipes, levels, dialogue, customers, rewards, and renovations independently of engine code. |
| Git | Version control | Tracks source, configuration, data, and approved assets; supports branches, review, rollback, and release tags. |
| Android SDK / ADB | Device toolchain | Compiles Android targets, installs builds, captures logs, profiles devices, and verifies behavior across API levels. |
| Automated validators | Quality and content safety | Detects missing IDs, broken references, invalid recipes, impossible levels, and unsafe save changes before packaging. |
| Art and audio tools | Content production | Final tooling may include raster/vector art, animation, audio editing, and AI-assisted concept or placeholder generation under a unified style guide. |

## Build workflow

Validate Godot content and automated tests.

Export the Godot project as ultimate_sugar_rush.pck.

Copy the PCK into the Android app assets directory.

Compile the selected Android debug or release variant.

Install on devices or generate a signed Android App Bundle.

Run smoke tests and preserve build metadata for traceability.

# 6. Milestones and Delivery Plan

The milestones are ordered by risk reduction. Timing is indicative and should be recalibrated after staffing, asset strategy, and the vertical-slice content target are approved.

| ID | Milestone | Indicative Window | Exit Deliverable |
| --- | --- | --- | --- |
| M0 | Definition | 1–2 weeks | Game brief, architecture, content schemas, economy assumptions, performance targets, and vertical-slice acceptance criteria. |
| M1 | Android–Godot integration | 1–2 weeks | Godot boot scene launches from Android Studio; automated PCK-to-APK/AAB build path works on a physical device. |
| M2 | Core framework | 2–3 weeks | Scene routing, services, input abstraction, settings, save system, debug tools, and content database. |
| M3 | Merge prototype | 3–5 weeks | Playable board with spawning, dragging, merging, feedback, recovery, serialization, and two representative chains. |
| M4 | Cooking and orders | 3–5 weeks | Stations, recipes, customers, order fulfillment, level objectives, rewards, and tutorial hooks. |
| M5 | Vertical slice | 4–6 weeks | Five to fifteen polished levels, first story arc, first renovation, final-direction UI, audio, accessibility basics, and external playtest. |
| M6 | Café metagame | 4–6 weeks | Renovation stages, decoration choices, recipe book, mastery, reputation, progression, and expanded customer systems. |
| M7 | Content production | 8–14 weeks | Representative launch volume of levels, recipes, merge chains, characters, story, rooms, art, and audio. |
| M8 | Alpha and balancing | 4–6 weeks | Feature-complete build, device matrix, economy tuning, save migrations, performance optimization, and issue burn-down. |
| M9 | Beta and release | 4–6 weeks | Content lock, signed AAB, store assets, privacy disclosures, closed testing, staged rollout, monitoring, and hotfix readiness. |

PLANNING NOTE The sequence above represents approximately 34–55 calendar weeks for a small team working largely sequentially. Parallel art, audio, narrative, level design, and engineering can shorten elapsed time, while a solo code-first approach will typically extend it.

## Vertical-slice acceptance criteria

A new player completes the tutorial without developer assistance.

The merge, cooking, order, reward, and renovation loop is complete and enjoyable.

Progress survives restart, process death, and application updates using the tested save version.

The build holds its target frame rate on an agreed lower-midrange Android device.

The project produces both installable debug builds and a signed internal-test AAB.

Test feedback supports continuing production rather than rethinking the central loop.

# 7. Quality, Accessibility, and Release Readiness

## Quality strategy

| Area | Minimum Standard |
| --- | --- |
| Gameplay correctness | Automated tests cover merge rules, recipes, rewards, level goals, purchases, save migrations, and deterministic generation. |
| Content integrity | Build-time validation catches duplicate IDs, missing references, impossible requirements, and incomplete localization keys. |
| Device coverage | Testing includes API 24, a current API emulator, a low-memory physical phone, tall and narrow screens, and interruption scenarios. |
| Performance | Stable 60 FPS during ordinary play where practical, graceful 30 FPS fallback, bounded effects, controlled memory, and responsive loading. |
| Persistence | Atomic save writes, backup recovery, versioned migrations, autosave, and explicit tests for interrupted or corrupted writes. |
| Release safety | Signed AAB, upgrade testing, crash/ANR monitoring, privacy disclosures, staged rollout, and a prepared hotfix path. |

## Accessibility commitments

Merge states communicate through shape, motion, and iconography—not color alone.

Reduced-motion and screen-shake settings are available from the first polished slice.

Music, sound effects, dialogue, and haptic feedback have independent controls.

Core play supports an alternative tap-select/tap-place interaction if drag input is difficult.

Text and touch targets remain legible at real phone scale and respect safe areas.

Tutorials can be replayed and dialogue can be skipped or displayed at adjustable speed.

## Release artifacts

Versioned source repository and tagged release commit.

Signed Android App Bundle and installable test APK.

Release notes, known-issues list, privacy/data-safety documentation, and store assets.

Validated save migration path from previous test builds.

Crash monitoring dashboard, rollout checklist, and hotfix procedure.

# 8. Key Risks and Mitigations

| Risk | Priority | Mitigation |
| --- | --- | --- |
| Content volume | High | Prove the loop with a small vertical slice; use stable IDs, reusable templates, validators, and data-driven definitions before scaling. |
| Game feel | High | Prioritize touch response, animation timing, haptics, audio layers, and device playtests during the merge prototype—not at the end. |
| Scope growth | High | Use milestone exit gates; defer online, social, live-ops, and complex monetization until the core loop is validated. |
| Android integration | Medium | Pin compatible Godot/Android dependencies; prove lifecycle, PCK packaging, Gradle builds, and signed AAB output in M1. |
| Save corruption | Medium | Use atomic writes, rolling backups, schema versions, migrations, and automated interrupted-write tests. |
| Performance fragmentation | Medium | Set a lower-midrange reference device, choose the compatibility renderer initially, and profile throughout production. |
| Economy imbalance | Medium | Instrument level outcomes, simulate sources and sinks, and keep purchases optional until nonpaying progression is healthy. |
| Art inconsistency | Medium | Approve a style guide and representative asset set before commissioning or generating large volumes of food and décor art. |

## Assumptions requiring confirmation

Portrait orientation and Android-first launch remain the product direction.

The initial release is offline-first and does not require user accounts.

GDScript is acceptable as the primary gameplay language.

The current Android Studio project remains the release host rather than being replaced by a standalone Godot export project.

Final launch scope, staffing, budget, content volume, and monetization model will be approved after the vertical slice.

# 9. Immediate Next Steps

Approval of this proposal should initiate the definition and integration milestones. The objective is to reach a device-running foundation quickly, then focus the majority of early iteration on whether merging, cooking, serving, and renovating feel satisfying together.

| Step | Action | Result |
| --- | --- | --- |
| 1 | Approve product baseline | Confirm portrait format, offline-first behavior, initial audience, vertical-slice recipes, and monetization constraints. |
| 2 | Establish technical baseline | Pin the stable Godot version, Android library, application ID strategy, renderer, minimum device, and build environments. |
| 3 | Create project skeleton | Add the /game, /tools, and /docs structure; establish Godot scenes, services, content schemas, and coding conventions. |
| 4 | Complete Android embedding | Host Godot from the existing Android app and automate PCK generation, asset copying, APK assembly, and device launch. |
| 5 | Build the merge prototype | Implement the 6×8 board, lemonade and cupcake chains, touch feedback, saving, debug tools, and gameplay tests. |
| 6 | Review the first playable | Evaluate enjoyment, readability, performance, integration stability, and scope before committing to full vertical-slice production. |

RECOMMENDATION Begin with Milestones M0 and M1. They create a durable production foundation and expose integration risks before substantial gameplay and content work begins.

## Approval checkpoint

Once the product assumptions and vertical-slice target are confirmed, implementation can proceed phase by phase against the exit criteria in this proposal. Each milestone should end with a working build, reviewable deliverables, documented decisions, and an explicit go/no-go decision for the next scope increase.

## References

Godot Engine documentation — Godot Android library and embedding guidance: https://docs.godotengine.org/en/stable/tutorials/platform/android/android_library.html

Godot Engine documentation — Exporting for Android: https://docs.godotengine.org/en/latest/tutorials/export/exporting_for_android.html

Existing Ultimate Sugar Rush Android Studio repository configuration reviewed August 3, 2026.